## Sheet1
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42979 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Etat de l'art | 2017-09-01 | 2017-09-04 | 3 | 2.4 | 0.6 | 80%
Choix des composants et comparatifs | 2017-09-04 | 2017-09-06 | 2 | 2 | 0 | 100%
Réalisation de la schématique du circuit | 2017-09-04 | 2017-09-14 | 10 | 10 | 0 | 100%
Routage du circuit | 2017-09-14 | 2017-09-24 | 10 | 10 | 0 | 100%
Check DRC du circuit | 2017-09-25 | 2017-09-26 | 1 | 1 | 0 | 100%
Test avec les cartes de développement (LoRa + BLE) | 2017-09-20 | 2017-10-10 | 20 | 10 | 10 | 50%
Liste du matériel à commander | 2017-09-26 | 2017-09-28 | 2 | 0.4 | 1.6 | 20%
Montage SmartCanton DevBox | 2017-10-10 | 2017-10-12 | 2 | 0 | 2 | 0%
Débuggage | 2017-10-12 | 2017-10-15 | 3 | 0 | 3 | 0%
Configuration du module LoRa | 2017-10-15 | 2017-10-25 | 10 | 0 | 10 | 0%
Configuration du module Bluetooth | 2017-10-15 | 2017-10-25 | 10 | 0 | 10 | 0%
Test du LoRa avec la DGSI | 2017-10-25 | 2017-11-14 | 20 | 0 | 20 | 0%
Tests des sensors de la carte | 2017-10-25 | 2017-11-14 | 20 | 0 | 20 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.