## Prediction
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42979 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Etat de l'art | 2017-09-01 | 2017-09-11 | 10 | 8 | 2 | 80%
Choix des composants et comparatifs | 2017-09-04 | 2017-09-09 | 5 | 5 | 0 | 100%
Réalisation de la schématique du circuit | 2017-09-04 | 2017-09-14 | 10 | 10 | 0 | 100%
Routage du circuit | 2017-09-14 | 2017-09-24 | 10 | 10 | 0 | 100%
Check DRC du circuit | 2017-09-25 | 2017-09-26 | 1 | 1 | 0 | 100%
Test avec les cartes de développement (LoRa + BLE) | 2017-09-20 | 2017-10-10 | 20 | 20 | 0 | 100%
Liste du matériel à commander | 2017-09-26 | 2017-09-28 | 2 | 2 | 0 | 100%
Montage SmartCanton DevBox | 2017-10-10 | 2017-10-12 | 2 | 2 | 0 | 100%
Débuggage carte électronique | 2017-10-12 | 2017-10-17 | 5 | 5 | 0 | 100%
Tests des sensors de la carte | 2017-10-15 | 2017-10-25 | 10 | 10 | 0 | 100%
Documentation des use cases | 2017-10-18 | 2017-10-20 | 2 | 2 | 0 | 100%
Test du LoRa avec le réseau DGSI | 2017-10-18 | 2017-10-21 | 3 | 3 | 0 | 100%
Etude et documentation de sécurité du Bluetooth | 2017-10-22 | 2017-11-01 | 10 | 1 | 9 | 10%
Analyse d'une API de communication entre les deux microcontrôleur (LoRa <-> BLE) | 2017-10-25 | 2017-10-30 | 5 | 0 | 5 | 0%
Programmation de l'API de communication entre microcontrôleurs | 2017-10-30 | 2017-11-09 | 10 | 0 | 10 | 0%
Mise en place de librairies pour la communication avec les différents périphériques | 2017-10-30 | 2017-11-29 | 30 | 0 | 30 | 0%
Use case deployment APPKEY Bluetooth : Analyse sur l'implémentation | 2017-11-10 | 2017-11-15 | 5 | 0 | 5 | 0%
Use case deployment APPKEY : Programmation KW41z + LoRa | 2017-11-15 | 2017-12-05 | 20 | 0 | 20 | 0%
Use case deployment APPKEY : Programmation serveur REST de partage de clés | 2017-12-01 | 2017-12-11 | 10 | 0 | 10 | 0%
Use case déployement APPKEY : App android | 2017-12-01 | 2017-12-11 | 10 | 0 | 10 | 0%
Use case tracking GPS : Analyse sur l'implémentation | 2017-12-11 | 2017-12-12 | 1 | 0 | 1 | 0%
Use case tracking GPS : Programmation KW41z | 2017-12-12 | 2017-12-15 | 3 | 0 | 3 | 0%
Use case tracking GPS : Programmation LoRa | 2017-12-13 | 2017-12-16 | 3 | 0 | 3 | 0%
Use case tracking GPS : Application de visualisation | 2017-12-14 | 2017-12-17 | 3 | 0 | 3 | 0%
Use case scanner Bluetooth : Analyse sur l'implémentation | 2017-12-17 | 2017-12-19 | 2 | 0 | 2 | 0%
Use case scanner Bluetooth : Programmation KW41z | 2017-12-19 | 2017-12-24 | 5 | 0 | 5 | 0%
Use case scanner Bluetooth : Programmation LoRa | 2017-12-22 | 2017-12-25 | 3 | 0 | 3 | 0%
Use case scanner Bluetooth : Application de visualisation | 2017-12-26 | 2018-01-05 | 10 | 0 | 10 | 0%
Use case all sensors : Analyse sur l'implémentation | 2018-01-03 | 2018-01-05 | 2 | 0 | 2 | 0%
Use case all sensors : Programmation KW41z | 2018-01-05 | 2018-01-10 | 5 | 0 | 5 | 0%
Use case all sensors : Programmation LoRa | 2018-01-10 | 2018-01-11 | 1 | 0 | 1 | 0%
Use case all sensors : Application de visualisation | 2018-01-11 | 2018-01-14 | 3 | 0 | 3 | 0%
Documentation globale du projet | 2017-09-01 | 2018-01-29 | 150 | 7.5 | 142.5 | 5%
Documentation en profondeur du projet | 2018-01-01 | 2018-01-31 | 30 | 0 | 30 | 0%
Relecture et correction du rapport | 2017-01-30 | 2017-02-09 | 10 | 0 | 10 | 0%
0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Real
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42979 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Etat de l'art | 2017-09-01 | 2017-09-11 | 10 | 8 | 2 | 80%
Choix des composants et comparatifs | 2017-09-04 | 2017-09-09 | 5 | 5 | 0 | 100%
Réalisation de la schématique du circuit | 2017-09-04 | 2017-09-14 | 10 | 10 | 0 | 100%
Routage du circuit | 2017-09-14 | 2017-09-24 | 10 | 10 | 0 | 100%
Check DRC du circuit | 2017-09-25 | 2017-09-26 | 1 | 1 | 0 | 100%
Test avec les cartes de développement (LoRa + BLE) | 2017-09-20 | 2017-10-10 | 20 | 20 | 0 | 100%
Liste du matériel à commander | 2017-09-26 | 2017-09-28 | 2 | 2 | 0 | 100%
Montage SmartCanton DevBox | 2017-10-10 | 2017-10-12 | 2 | 2 | 0 | 100%
Débuggage carte électronique | 2017-10-12 | 2017-10-17 | 5 | 5 | 0 | 100%
Tests des sensors de la carte | 2017-10-15 | 2017-10-25 | 10 | 10 | 0 | 100%
Documentation des use cases | 2017-10-18 | 2017-10-20 | 2 | 2 | 0 | 100%
Test du LoRa avec le réseau DGSI | 2017-10-18 | 2017-10-21 | 3 | 3 | 0 | 100%
Etude et documentation de sécurité du Bluetooth | 2017-10-22 | 2017-11-01 | 10 | 1 | 9 | 10%
Analyse d'une API de communication entre les deux microcontrôleur (LoRa <-> BLE) | 2017-10-25 | 2017-10-30 | 5 | 0 | 5 | 0%
Programmation de l'API de communication entre microcontrôleurs | 2017-10-30 | 2017-11-09 | 10 | 0 | 10 | 0%
Mise en place de librairies pour la communication avec les différents périphériques | 2017-10-30 | 2017-11-29 | 30 | 0 | 30 | 0%
Use case deployment APPKEY Bluetooth : Analyse sur l'implémentation | 2017-11-10 | 2017-11-15 | 5 | 0 | 5 | 0%
Use case deployment APPKEY : Programmation KW41z + LoRa | 2017-11-15 | 2017-12-05 | 20 | 0 | 20 | 0%
Use case deployment APPKEY : Programmation serveur REST de partage de clés | 2017-12-01 | 2017-12-11 | 10 | 0 | 10 | 0%
Use case déployement APPKEY : App android | 2017-12-01 | 2017-12-11 | 10 | 0 | 10 | 0%
Use case tracking GPS : Analyse sur l'implémentation | 2017-12-11 | 2017-12-12 | 1 | 0 | 1 | 0%
Use case tracking GPS : Programmation KW41z | 2017-12-12 | 2017-12-15 | 3 | 0 | 3 | 0%
Use case tracking GPS : Programmation LoRa | 2017-12-13 | 2017-12-16 | 3 | 0 | 3 | 0%
Use case tracking GPS : Application de visualisation | 2017-12-14 | 2017-12-17 | 3 | 0 | 3 | 0%
Use case scanner Bluetooth : Analyse sur l'implémentation | 2017-12-17 | 2017-12-19 | 2 | 0 | 2 | 0%
Use case scanner Bluetooth : Programmation KW41z | 2017-12-19 | 2017-12-24 | 5 | 0 | 5 | 0%
Use case scanner Bluetooth : Programmation LoRa | 2017-12-22 | 2017-12-25 | 3 | 0 | 3 | 0%
Use case scanner Bluetooth : Application de visualisation | 2017-12-26 | 2018-01-05 | 10 | 0 | 10 | 0%
Use case all sensors : Analyse sur l'implémentation | 2018-01-03 | 2018-01-05 | 2 | 0 | 2 | 0%
Use case all sensors : Programmation KW41z | 2018-01-05 | 2018-01-10 | 5 | 0 | 5 | 0%
Use case all sensors : Programmation LoRa | 2018-01-10 | 2018-01-11 | 1 | 0 | 1 | 0%
Use case all sensors : Application de visualisation | 2018-01-11 | 2018-01-14 | 3 | 0 | 3 | 0%
Documentation globale du projet | 2017-09-01 | 2018-01-29 | 150 | 7.5 | 142.5 | 5%
Documentation en profondeur du projet | 2018-01-01 | 2018-01-31 | 30 | 0 | 30 | 0%
Relecture et correction du rapport | 2017-01-30 | 2017-02-09 | 10 | 0 | 10 | 0%
0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.